## Sheet1
|  | Duration | Resource
1 | Garage conversion into playroom
2 | Garage cleanout
3 | Clean out the garage | 2 | Homeowner
4 | Sell unwanted items | 1 | Homeowner
5 | Take trash to the dump | 1 | Homeowner
6 | Demolition
7 | Tear out all existing walls | 1 | Crew
8 | Tear out shelving | 1 | Crew
9 | Remove garage door/unit | 1 | Crew
10 | Sell garage door/unit online | 1 | Homeowner
11 | Framing
12 | Frame out new wall for front door/windows | 2 | Contractor
13 | Install insulation | 1 | Crew
14 | Plumbing
15 | Move hot water heater | 2 | Crew
16 | Install drainline | 1 | Contractor
17 | Test plumbing | 1 | Contractor
18 | Electrical
19 | Install new breakers | 2 | Contractor
20 | Wire new outlets | 3 | Crew
21 | Install lights and fan | 2 | Crew
22 | Test electrical | 1 | Contractor
23 | Windows
24 | Purchase windows | 1 | Homeowner
25 | Install windows | 1 | Contractor
26 | Drywall
27 | Install drywall | 3 | Crew
28 | Tape and float seams/holes | 1 | Crew
29 | Sand to finish | 1 | Crew
30 | Painting/Finishing
31 | Apply texture to walls and ceiling | 1 | Crew
32 | Paint walls and ceiling | 1 | Crew
33 | Siding
34 | Install exterior siding | 2 | Contractor
35 | Paint siding | 1 | Crew
36 | Other
37 | Level concrete drive | 2 | Crew
38 | Install A/C unit | 1 | Contractor
39 | Insulate attic | 1 | Crew
40 | House walkthrough | 0 | Homeowner
41 | Punchlist | 1 | Contractor